## Sheet1
Assumption
Employees | 500
Customers | 100000
Annual Revenue | 50000000
Analysis Period | 3 Years
Web Servers | 4
Application Servers | 4
Database Servers | 2
Storage | 20TB
IT Team | 8
Cloud Provider | AWS
AWS Region | N. Virginia
On-Premise Cost
Cost Category | Year 1 | Year 2 | Year 3
Server Hardware | 80000 | 0 | 0
Storage hardware | 20000 | 0 | 0
Data centre costs | 30000 | 30000 | 30000
Electricity/Cooling | 15000 | 15000 | 15000
Hardware Maintenance | 20000 | 20000 | 20000
Backup/Disaster recovery | 10000 | 10000 | 10000
IT infrastructure | 80000 | 80000 | 80000
Total cost | 255000 | 155000 | 155000
3-Year Total | 51230518
AWS Cost
AWS Component | Year 1 | Year 2 | Year 3
EC2 | 2915 | 2915 | 2915
RDS | 286.92 | 286.92 | 286.92
S3 | 1380 | 1380 | 1380
Load Balancer | 260 | 260 | 260
Data Transfer | 972 | 972 | 972
CloudWatch | 150 | 150 | 150
Backup | 300 | 300 | 300
AWS support | 348 | 348 | 348
Total Cost | 6611.92 | 6611.92 | 6611.92
3-Year Total | 19835.76
Migration Cost
Migration Cost | Estimated Cost
Migration planning | 20000
Application assessment | 15000
Data migration | 10000
Staff training | 10000
External Consultancy | 25000
Testing | 10000
Temporary dual-runnning | 20000
Total | 110000
Total cost of Comparison
On-Premise | 565000
AWS | 19835.76
Migration | 110000
Cloud + Migration | 129835.76
Risk | Likelihood | Impact | Mitigation
Data loss during migration | Medium | High | Backup and data validation
AWS Cost | Medium | Medium | Budgets and monitoring
Security misconfigurations | Medium | Medium | IAM, testing, security groups
Migration takes longer that expected | Medium | Medium | Pilot migration and phased rollout